## Sprint burn-down chart
Days | Estimate to complete | Ideal Burn-Down | Trend
Day 1 | 450 | 450 | 450
Day 2 | 410 | 400 | 410
Day 3 | 330 | 350 | 330
Day 4 | 320 | 300 | 320
Day 5 | 260 | 250 | 260
Day 6 | 230 | 200 | 230
Day 7 |  | 150 | 186
Day 8 |  | 100 | 142
Day 9 |  | 50 | 98
Review |  | 0 | 54
Example Burn-Down Chart 1
Increase or decrease the days in column A as suits your Sprint Duration.
Enter the total planned hours in cell B2 (the yellow cell).
The ideal Burn-Down rate is calculated and plotted for you.
At the beginning of each subsequent day, enter the estimate to complete of all remaining work (purple cells).
The trend is calculated and plotted for you.
When progress is good, the line will dip below the ideal line, and reach 0 earlier.
When progress is not so good, the line will drift above the ideal line, and will not reach 0 by the end of the Sprint.